STAGE Ruixing ZHENG

Topic: NAMED ENTITY RECOGNITION AND ENTITY LINKING FOR HISTORICAL TEXTS
Co-supervision: Carlos-Emiliano González-Gallardo and Cyril Derunz
Dates: from April 17th  to November 6st – 35h / week (126 working days)

Gratification: 3 969€ net (882h – 4€50/h)

Dates:

- Weeks of 27/07 and 03/08 and 10/08 are off

- Welcome: Friday, April 17th – 9am at EPU

- Kick-off meeting: Friday, April 17th – 10am at Polytech

- Known unavailabilities:

  - Carlos

    - April 23rd  – May 4th (away, access to mail from time to time)

    - May 11th – May 15th (away but reachable)

    - June 26th – July 3th (away but reachable)

- 20th June end of CAF

- 1st July 100% Tours

- 23rd September end of Titre de Sejour

Methodology:

- Workplace: salle RFAI / CESR

- Weekly meeting: Monday 3pm (visio or EPU)

- Weekly mail (Sunday 23h59) – [planned – done – todo]

- Team & Git: to create

Tasks:

- Context/motivation

- Data study and annotation

- State of the Art

- Old-school named entity recognition (NER) and entity linking (EL)

- Neural NER and EL

- Evaluation (qualitative, quantitative)

- (Benchmark / Generalisation)

- Research article – Internship report

- Application for CESR (UI)

Goals:

- Main:

  - Data annotation for NER

  - Workflow for detecting, classifying, and linking entities -> developer documentation

  - Tool / IHM -> user documentation

  - Tests and results on the PRIMA data

- Optional:

  - Research article

  - Perspectives: entity detection in manuscripts using VLMs

# Resources

1. Software and Technical Tools

- Zotero (bibliography)

  - https://www.zotero.org/

- Overleaf

- INCEpTION (A semantic annotation platform offering intelligent assistance and knowledge management)

  - https://inception-project.github.io/

2. Knowledge graphs and authority records

- Wikidata

  - https://www.wikidata.org

- VIAF (Fichier d'autorité international virtuel)

  - https://viaf.org/fr

3. Selected Bibliographical References

- https://hal.science/hal-05248289v1

- https://univ-tours.hal.science/hal-04662000/

- https://ceur-ws.org/Vol-3180/paper-84.pdf